## Timed Deliverables
enter your "Book title" |  | Author name: | enter your name here
OVERALL TIMING | DELIVERABLE | RESPONSIBILITY | DUE DATE | STATUS | DETAILS
| Launch date - please enter your date here - year, month, day |  | 2022-12-29
3 months prior | Require PDF of book | Hasmark | 2022-09-30
-90 | Require jpg of book cover or Initiate cover design | Hasmark | 2022-09-30
| Headshot of client for Author Photo | Hasmark | 2022-09-30
| Admin to greet and send questionnaire. | Hasmark | 2022-09-30
| Set up first Intro Zoom call | Hasmark | 2022-09-30
| HH to send approval form | Hasmark | 2022-09-30
| Review manuscript for completeness | Hasmark | 2022-09-30
| Obtain ISBN, create copyright page & prep manuscript for editing | Hasmark | 2022-09-30
| Identify placeholders for any elements missing | Hasmark | 2022-09-30
| Request missing elements from client. | Hasmark | 2022-09-30
| Basecamp Initiated | Hasmark | 2022-09-30
| Marketing Commences | Hasmark | 2022-09-30
| Questionnaire completed and returned to Admin | Hasmark | 2022-09-30
| HH receives approval to include page in book | Hasmark | 2022-09-30
| Questionnaire uploaded to basecamp | Hasmark | 2022-09-30
| AKDP Form is sent to client | Hasmark | 2022-09-30
EDITING:
| Determine level of edit. | Hasmark | 2022-09-30
| Send Manuscript to editor. | Hasmark | 2022-09-30
| First round of edits are sent to author | Hasmark | 2022-09-30
| Author feedback/edits are returned to Editor for cleanup | Hasmark | 2022-09-30
| Editor Returns clean, edited manuscript ready for Proofread | Hasmark | 2022-09-30
2 months | PROOFREADING:
prior to launch | Manuscript sent to chosen Proofreader | Hasmark | 2022-10-30
-60 | Proofreader returns manuscript to Hasmark/Hasmark sends to client for final editing approval | Hasmark | 2022-10-30
| Client Approves manuscript can move to Layout (Proofreader makes any changes first) | Hasmark | 2022-10-30
| Proofreader/Editor to create text for back cover (or request from author). | Hasmark | 2022-10-30
| Ensure that each and every element of the book is edited before sending to layout | Hasmark | 2022-10-30
| Request Endorsements | Hasmark | 2022-10-30
1 mth | LAYOUT:
prior to launch | Ensure any special instructions, illustrations or images are received by designer | Hasmark | 2022-11-29
-30 | Author chopses endoresment(s) for cover | Hasmark | 2022-11-29
| Ensure full cover text is approved as well as final design | Hasmark | 2022-11-29
| Round 1 of layout is sent to Client for feedback | Hasmark | 2022-11-29
| Client feedback is returned to Layout artist; layout artist to make changes | Hasmark | 2022-11-29
| Manuscript is returned to client for FINAL APPROVAL | Hasmark | 2022-11-29
| Client approved and final files are created. | Hasmark | 2022-11-29
UPLOAD TO AKDP:
3 weeks | AKDP account is created | Hasmark | 2022-12-08
prior to launch | Book is uploaded to AKDP | Hasmark | 2022-12-08
-21 | If approved, book is live on amazon.com within 24 hours; then will populate all other countries thereafter | Hasmark | 2022-12-08
2 weeks | Categories determined & submitted to Amazon | Hasmark | 2022-12-15
prior to launch | Author Central Account created and populated | Hasmark | 2022-12-15
-14 | confirm categories are set up & Amazon page looks good | Hasmark | 2022-12-15
1 week | BESTSELLER LAUNCH:
prior to launch | Create client spreadsheet | HPI Marketing | 2022-12-22
-7 | Add all amazon links to spreadsheet | HPI Marketing | 2022-12-22
| Send author all sell site links | HPI Marketing | 2022-12-22
| confirm promotion page is in draft and all links are working efficiently | HPI Marketing | 2022-12-22
| record rankings from sell sites | HPI Marketing | 2022-12-28
Week of | Send RRC newsletter | HPI Marketing | 2022-12-28
Launch | track progress of book ranking on amazon and B&N, screen dump any #1 rankings | HPI Marketing | 2022-12-28
-1 | send report of best rankings to client | HPI Marketing | 2022-12-28
|  | HPI Marketing | 2022-12-28
Week after | Send badge to client | HPI Marketing | 2023-01-05
Launch | Cover w/Badge is uploaded to AKDP w/client approval | HPI Marketing | 2023-01-05
7 | Certificate is sent | HPI Marketing | 2023-01-05
| Send the What's Next document | HPI Marketing | 2023-01-05
| Acquire endorsement of service for our clients | HPI Marketing | 2023-01-05
https://hasmarkpublishing.com